## Sheet1
Report: Project Report |  | Supervised by: Morenikeh Taylor
Date: 03/07/2020
Vehicle Request Form - DEVELOPER - Salim M. Jalloh (Intern) |  |  | START DATE - July 2nd, 2020
ACTIVITY | WORKDONE | PRESENT STATUS | RESOURCES | TIMELINE
VEHICLE REQUEST FORM | 1. Welcome page and login User Interface | Completed | none | July 2nd - July 3rd
| 2. Create User and Admin |  | none | July 3rd - July 7th
| 3. User authentication and authorization. |  | none
| 4. Keep a log of when a user and driver profile was created and who created the user. |  | none | July 7th - July 8th
| 5. Vehicle request form User interface for users |  | none | July 8th - July 10th
| 6. Vehicle request form User Interface for Line Managers |  | none
| 7. Fleet Coordinator's Dashboard User Interface |  | none | July 10th - July 12th
| 8. Vehicle allocation logic |  | Resources from Morenikeh and Kamal | July 13th - July 22nd
| 9. Fleet Coordinators escalation and archive logic |  | Resources from Morenikeh and Kamal | July 22nd - July 26th
| 10. Make a log of daily request |  | none